## Product Backlog
ID | Epic | User Story | Acceptance Criteria | Priority | Story Points | Status
US1.1 | Gestion User | As a visitor, I want to create an account so that I can use the platform. | • User can register with email and password • Required fields are validated • Password is stored securely (hashed) • Default role = Guest | High | 3 | To Do
US1.2 | Gestion User | As a user, I want to log in and log out so that my account is secure. | • User can authenticate with credentials • Session management implemented • Secure logout functionality • Session timeout after inactivity | High | 2 | To Do
US1.3 | Gestion User | As a host, I want to request host status so that I can publish logements and tools. | • Host request form available • Admin receives notification • Approval workflow implemented • User role updated upon approval | Medium | 5 | To Do
US1.4 | Gestion User | As an admin, I want to monitor suspicious user activity so that I can detect scammers. | • System logs abnormal actions • Admin can view flagged users • Flagged users are marked with warning status • Activity log includes timestamps and details | High | 8 | To Do
US1.5 | Gestion User | As an admin, I want to suspend or ban abusive users so that the platform remains safe. | • Admin can suspend or ban users • Suspended users cannot reserve or publish • Banned users cannot log in • All actions are logged | High | 5 | To Do
US1.6 | Gestion User | As an admin, I want to manage user roles and account status so that I can control access. | • Admin can view all users • Admin can modify user roles • Admin can activate/deactivate accounts • Changes are logged and auditable | Medium | 3 | To Do
US2.1 | Gestion Foyer | As a host, I want to add a logement with category, price, and location so that guests can book it. | • Required fields: title, price, location, category • Images added via URL • Logement visible to guests • Validation for all required fields | High | 8 | To Do
US2.2 | Gestion Foyer | As a host, I want to edit or delete my logement so that I can keep my listings updated. | • Host can edit all logement details • Host can delete listings • Soft delete with confirmation • Changes reflect immediately | High | 5 | To Do
US2.3 | Gestion Foyer | As a guest, I want to view logement details so that I can decide before reserving. | • Detailed view page with all information • Images gallery • Location map • Availability calendar | High | 5 | To Do
US2.4 | Gestion Foyer | As a guest, I want to filter logements by category, price, and location so that I can find what I need. | • Filter by category • Filter by price range • Filter by location • Multiple filters can be combined | High | 8 | To Do
US2.6 | Gestion Foyer | As an admin, I want to review reported or problematic listings so that I can moderate only when necessary. | • Guests can report listings • Admin dashboard shows reported listings • Admin can hide, warn, or delete • Actions are logged | Medium | 5 | To Do
US3.1 | Gestion Matériel | As a host, I want to add tools for rent so that guests can rent local equipment. | • Host adds tool with name, category, price • Tool availability status • Tool visible in search • Image upload capability | Medium | 5 | To Do
US3.2 | Gestion Matériel | As a host, I want to define tool rental periods and pricing so that guests can rent tools independently. | • Define hourly/daily/weekly rates • Set minimum/maximum rental periods • Availability calendar management • Pricing rules validation | Medium | 5 | To Do
US3.3 | Gestion Matériel | As a guest, I want to browse available tools so that I can rent what I need. | • Tool catalog with search • Filter by category and price • Display availability status • Show tool details and ratings | Medium | 5 | To Do
US3.4 | Gestion Matériel | As a guest, I want to reserve a tool for specific dates so that I can use it when needed. | • Guest selects rental dates • System checks availability • Prevent overlapping reservations • Reservation stored with confirmed status | High | 8 | To Do
US3.5 | Gestion Matériel | As the system, I want to apply tool category rules and validation so that tools are classified automatically. | • Automatic category suggestion • Validation rules for tool data • Category hierarchy support • Data integrity checks | Low | 3 | To Do
US3.6 | Gestion Matériel | As a guest, I want to rent tools without booking a logement so that I can access local equipment easily. | • Standalone tool rental flow • Independent from logement booking • Separate checkout process • Tool-only reservation management | Medium | 5 | To Do
US3.7 | Gestion Matériel | As an admin, I want to review tools that are reported or flagged so that I only intervene in suspicious cases. | • Flagging system for tools • Admin moderation dashboard • Review and action workflow • Communication with tool owner | Medium | 3 | To Do
US4.1 | Gestion Services | As a host, I want to define available services so that guests can request them. | • Create service catalog • Define service pricing • Set service availability • Service descriptions and terms | Medium | 5 | To Do
US4.2 | Gestion Services | As a guest, I want to request a service so that my stay is more comfortable. | • Browse available services • Request service with details • Specify date/time preferences • Track request status | Medium | 3 | To Do
US4.3 | Gestion Services | As a host, I want to manage service requests so that I can accept or reject them. | • View all service requests • Accept or reject with reason • Notification to guest • Request history tracking | Medium | 5 | To Do
US4.4 | Gestion Services | As an admin, I want to review reported services so that I can moderate only when necessary. | • Service reporting system • Admin review interface • Moderation actions • Communication workflow | Low | 3 | To Do
US5.1 | Gestion Réservation | As a guest, I want to reserve a logement for specific dates so that I can plan my stay. | • Select start/end dates • Check availability • Prevent double booking • Calculate total price • Status = Confirmed | Critical | 8 | To Do
US5.2 | Gestion Réservation | As a guest, I want to cancel a reservation within allowed rules (e.g. at least 7 days before). | • System checks cancellation deadline • Allow or refuse based on policy • Update reservation status • Notify host • Refund processing | High | 5 | To Do
US5.3 | Gestion Réservation | As a host, I want to see all reservations for my logements so that I can manage availability. | • Dashboard with all reservations • Filter by property and status • Calendar view • Export functionality | High | 5 | To Do
US5.4 | Gestion Réservation | As the system, I want to prevent double booking so that two users cannot reserve the same resource. | • Real-time availability checking • Lock mechanism during booking • Conflict detection • Automatic conflict resolution | Critical | 8 | To Do
US5.5 | Gestion Réservation | As the system, I want to enforce cancellation policies so that hosts are protected. | • Policy rules engine • Automatic policy application • Refund calculation logic • Policy documentation display | High | 5 | To Do
US6.1 | Gestion Avis | As a guest, I want to leave a review and rating so that I can share my experience. | • Only after completed reservation • Rating 1 to 5 • Comment required • Review visible after submission | High | 5 | To Do
US6.2 | Gestion Avis | As a guest, I want to see other users' reviews so that I can make better decisions. | • Display all reviews for listing • Show average rating • Sort by date or rating • Pagination for many reviews | High | 3 | To Do
US6.3 | Gestion Avis | As a host, I want to view feedback so that I can improve my services. | • View all reviews received • Response capability • Rating analytics • Trend analysis over time | Medium | 3 | To Do
US7.1 | Assistance Intelligente | As a guest, I want to receive recommended logements based on my budget and preferences. | • Suggest based on budget and category • At least 3 recommendations • Logic documented • Personalization based on history | Medium | 13 | To Do
US7.2 | Assistance Intelligente | As a guest, I want to receive recommended tools based on my needs. | • Tool recommendation engine • Based on booking location and type • Relevant suggestions • Explanation for recommendations | Low | 8 | To Do
US7.3 | Assistance Intelligente | As a guest, I want to receive suggested services based on my stay. | • Service suggestions based on logement • Contextual recommendations • Popular services highlighted • Smart bundling options | Low | 8 | To Do
US7.4 | Assistance Intelligente | As a host, I want to see an automatic summary of reviews. | • Analyze multiple reviews • Generate positive/negative summary • Update with new reviews • Key themes extraction | Low | 13 | To Do
US7.5 | Assistance Intelligente | As an admin, I want the system to flag potentially fraudulent behavior using automated rules. | • Apply fraud rules • Flag risky users • Show in admin dashboard • Log flag reasons • ML-based pattern detection | Medium | 13 | To Do

## Summary
Project Summary
Total User Stories: | 35
Total Story Points: | 0
Epics Overview:
Gestion User: | 6
Gestion Foyer: | 5
Gestion Matériel: | 7
Gestion Services: | 4
Gestion Réservation: | 5
Gestion Avis: | 3
Assistance Intelligente: | 5
Priority Breakdown:
Critical: | 2
High: | 14
Medium: | 14
Low: | 5